## Sheet1
ID | Name | Start Date | Possible Duration | Finished | Unfinished | Responsible | Notes | End Date
1 | Text To Speech Module | 2021-06-25 | 100 | 26 | 74 |  |  | 2021-10-03
1.1 | Select open source TTS model | 2021-06-06 | 30 | 30 | 0 |  |  | 2021-07-06
1.2 | Evaluate model’s suitability | 2021-07-07 | 30 | 14 | 16 |  |  | 2021-08-06
1.3 | Setup environment to get model running | 2021-07-08 | 30 | 13 | 17 |  |  | 2021-08-07
1.4 | Run tests | 2021-06-09 | 30 | 30 | 0 |  |  | 2021-07-09
1.5 | Integrate with other modules | 2021-06-10 | 30 | 30 | 0 |  |  | 2021-07-10
2 | Speech To Text Module | 2021-06-11 | 100 | 40 | 60 |  |  | 2021-09-19
2.1 | pick model / service to use | 2021-06-12 | 30 | 30 | 0 |  |  | 2021-07-12
2.2 | get the module running locally | 2021-06-13 | 30 | 30 | 0 |  |  | 2021-07-13
2.3 | integrate with other modules | 2021-06-14 | 30 | 30 | 0 |  |  | 2021-07-14
3 | Natural Language Understanding Module | 2021-06-15 | 100 | 36 | 64 |  |  | 2021-09-23
3.1 | Select dataset | 2021-06-16 | 30 | 30 | 0 |  |  | 2021-07-16
3.2 | Build Decision tree | 2021-06-17 | 30 | 30 | 0 |  |  | 2021-07-17
3.3 | Integrate DTree with | 2021-06-18 | 30 | 30 | 0 |  |  | 2021-07-18
3.4 | Integrate with other modules | 2021-06-19 | 30 | 30 | 0 |  |  | 2021-07-19
4 | Natural Language Generation Module | 2021-06-20 | 100 | 31 | 69 |  |  | 2021-09-28
4.1 | Create templates of response | 2021-06-21 | 30 | 30 | 0 |  |  | 2021-07-21
4.2 | Finetune the model | 2021-06-22 | 30 | 29 | 1 |  |  | 2021-07-22
4.3 | Integrate with other modules | 2021-07-01 | 20 | 20 | 0 |  |  | 2021-07-21
Notes: Please only fill "Start Date", "Possilbe Duration","Responsible"and "Notes" colums. DO NOT modify other units
Formulas:
Finished = IF([Possible Duration]>DATEDIF([Start Date],TODAY(),"d"),DATEDIF([Start Date],TODAY(),"d"),[Possible Duration])
End Date = [Start Date]+[Possible Duration]